## Start Here
Start Here – the next two weeks
Just the 'Now' tasks. Everything else waits on the Task List until it's its turn. Snapshot as of 1 Oct 2026.
ID | Section | Task | When | Owner | Done? | Notes
1 | 0. Monday & Claude Setup | Check Monday trial status and end date | Fri 2 Oct |  | ☐ | Cat – from the van
2 | 0. Monday & Claude Setup | Upgrade Monday to Pro, monthly billing | Fri 2 Oct |  | ☐ | Cat – call Charlotte for card
3 | 0. Monday & Claude Setup | Invite Yahya to Monday as Member (info@infovis.co.uk) | Fri 2 Oct |  | ☐ | Cat to email him once done
4 | 0. Monday & Claude Setup | Make sure Cat is a Monday admin | Fri 2 Oct |  | ☐
5 | 0. Monday & Claude Setup | Send Yahya samples: spreadsheet, task list, marketing plan, targets, enquiry tracker extract | Weekend |  | ☐ | This workbook covers the task list
6 | 0. Monday & Claude Setup | Setup day with Yahya, Cat and Charlotte | Mon 5 Oct |  | ☐
7 | 0. Monday & Claude Setup | Build marketing board – one group per brand | Mon 5 Oct |  | ☐ | Yahya
8 | 0. Monday & Claude Setup | Load this task list into Monday | Mon 5 Oct |  | ☐ | Yahya
9 | 0. Monday & Claude Setup | Build goals & targets dashboard for the Tuesday meeting | Mon 5 Oct |  | ☐ | Yahya
28 | 1. All Brands | Include BNC in every press release, for every brand | Ongoing |  | ☐ | Use BNC's marketing systems
30 | 1b. BNC Exhibition (end Oct) | Confirm exhibition date, venue, stand size and what's included | Now |  | ☐ | Date TBC – end of October
31 | 1b. BNC Exhibition (end Oct) | Find out what marketing BNC offers exhibitors – newsletters, social, website listings, press | Now |  | ☐
32 | 1b. BNC Exhibition (end Oct) | Get BNC logos, brand guidelines and exhibitor wording | Oct |  | ☐
33 | 1b. BNC Exhibition (end Oct) | Decide which brands we showcase and how – one Collective stand | Oct |  | ☐
43 | 1c. Venue Sourcing | Brainstorm our point of difference – every caterer wants the venues, why us? (Cat, Jessica, Lois) | Now |  | ☐ | Whole Collective as one supplier: food, drink, styling, staffing, wellness, Latino
44 | 1c. Venue Sourcing | Write the point of difference in one line, plus 3 proof points | Now |  | ☐
45 | 1c. Venue Sourcing | Build the target venue list – type, capacity, current caterer, contact | Now |  | ☐
48 | 1c. Venue Sourcing | Christmas packages for venues | Now |  | ☐ | Link with PenniBlack Christmas packages
55 | 1c. Venue Sourcing | Venue pipeline board in Monday – contacted, meeting, trial, on supplier list | Mon 5 Oct |  | ☐ | Ask Yahya
57 | 2. PenniBlack Catering & Events | Christmas campaign to existing followers – social posts | Oct–Dec |  | ☐ | Big follower base – use it
59 | 2. PenniBlack Catering & Events | Christmas packages with 'from £' prices | Oct |  | ☐
68 | 3. Free Spirit Wellness | Chase Momoko (Menier Venues) to confirm the date – push hard, nothing can be booked until it's set | Now |  | ☐ | Hoping for Wed 21 Oct
69 | 3. Free Spirit Wellness | Confirm which Menier team members are coming and agree the run of show | Once date set |  | ☐ | Purpose: the Menier team try it and review it
70 | 3. Free Spirit Wellness | Book workshop hosts – Ayurvedic scrubs, yoga, self-defence | Once date set |  | ☐ | Waiting on date
80 | 4. Pichi | Send Momoko (Menier Venues) the full attendee list from the Pichi launch | Mon 5 Oct |  | ☐ | Promised in Charlotte's email of 1 Oct – Cat
128 | 9. Systems & Admin | Team availability calendar in Monday – who's free to work when | Oct |  | ☐ | Quick win – ask Yahya

## Summary
PenniBlack Collective – Task Summary
Counts update automatically from the Task List tab.
Section | Now | Next | Later | Total | Done
0. Monday & Claude Setup | 9 | 4 | 0 | 13 | 0
1. All Brands | 1 | 12 | 3 | 16 | 0
1b. BNC Exhibition (end Oct) | 4 | 9 | 0 | 13 | 0
1c. Venue Sourcing | 5 | 9 | 0 | 14 | 0
2. PenniBlack Catering & Events | 2 | 8 | 1 | 11 | 0
3. Free Spirit Wellness | 3 | 7 | 2 | 12 | 0
4. Pichi | 1 | 1 | 7 | 9 | 0
5. Raquel's Staffing & Bar | 0 | 7 | 0 | 7 | 0
6. VENN Productions | 0 | 0 | 4 | 4 | 0
7. Be-Zing (Kids + Youth) | 0 | 9 | 14 | 23 | 0
8. The Edit (PBC Edit) | 0 | 0 | 5 | 5 | 0
9. Systems & Admin | 1 | 0 | 10 | 11 | 0
Total | 26 | 66 | 46 | 138 | 0
How to use
• Start Here: the next two weeks only. Cat works from this, not the full list.
• Task List: everything, grouped by brand. Filter by Stage = Now to see what's live. Owner, Stage and Status have dropdowns.
• Every Tuesday: Cat ticks off what's done, then moves the next 3–5 tasks per person from Next to Now.
• Once in Monday, each person uses 'My Work' to see only their own tasks.
• Built so Yahya can import it straight into Monday: Section = group, Task = item, other columns = Monday columns.
• Key dates: Free Spirit at the Menier Penthouse – hoping for Wed 21 Oct (awaiting Momoko). BNC exhibition – end of October (date TBC).
• Still to check: Be-Zing Kids award ceremony details.

## Team
PenniBlack Collective – Team & Roles
Rough seats, not fixed roles. October 2026.
Name | Seat | Strengths | Typical work | Works closely with | Starts | Monday | Claude
Charlotte | Founder | Vision, concepts, all brands | Own tasks in Monday – but doesn't run the system. Leads Be-Zing. | Cat, Yahya | Now | Yes | Premium
Cat (Catrin Dimond) | Chief of Marketing – runs Monday | Social media, photography, video, design, concepts & styling | Sets and manages everyone's tasks. Runs Tuesday meeting. Creates concepts (often off-site) and helps assemble them. Attends events, does case studies. | Lois (content & web), Jessica (concepts & sales) | Now | Yes – Admin | Premium
Lois Burton | Content, PR & Creative Lead | Art PR degree, high-end photo & video, writing | Web content, blogs, SEO, client experience (with Cat). PR. Leads Be-Zing marketing and The Edit. Attends fewer events. | Cat | End of October | Yes | Standard
Jessica | Sales & Events Manager | Client-facing, events, strong styling eye | Meets clients, sees spaces, brings concepts to life on site, styles her areas (e.g. bar). Goes to client meetings with Cat. Admin skills TBC. | Cat, Lois | Mid-October | Yes | TBC
Danelle van Tonder | Quotes & Client Liaison | Organised, client care | Quotes and client liaison – reactive. | Ana | Now | Yes | Standard
Ana | Quotes & Client Support (part-time) | Cost calculator trained | Assists Danelle on quotes and clients. Uses sales@ email. | Danelle | Now | Yes | No – review later
Alex | Systems & Events (flexible) | Business studies student, free days | Builds stock control system first (trial). Possibly more systems, packing, events, bar. | Charlotte, Yahya | When free | TBC | No
Raquel | Event Manager & Logistics | On the ground | Events, logistics, occasional site visits. Outside the admin system for now. Pichi input. | Steph, Ana | Now | View only / later | No
Yahya (InfoVis) | IT & Database Consultant | Systems integration | Monday structure, Claude connections, Xero, staff app review. | Cat, Charlotte | Mon 5 Oct | Member | Not yet
Jess & Dave | Collective partners – design | Design & styling eye | VENN Productions. Outside the admin system. | Charlotte | — | No | —
Steph | Runs Pichi | Latino culture | Pichi brainstorms and vision. Outside the admin system. | Raquel, Ana, Cat | — | No | —
How they pair up
• Cat + Lois: website content, blogs, writing, client experience, content & PR. They agree crossovers between them.
• Cat + Jessica: concepts, styling and sales. Cat creates the concept, Jessica brings it to life at the event. Client meetings together.
• Cat + Jessica + Lois: all brainstorm concepts and creative ideas.
• Danelle + Ana: quotes and client liaison (reactive).
• Rhythm: Cat sets tasks in Monday → Tuesday team meeting to review.

## Task List
PenniBlack Collective – Master Task List
Stage: Now = next 2 weeks · Next = rest of Oct–Dec · Later = 2027 / once Now and Next are moving. Priority 1 = money before Christmas · 2 = build the brands · 3 = systems. Owner left blank for Cat to allocate.
ID | Section | Workstream | Task | Priority | Stage | When | Owner | Status | Notes
1 | 0. Monday & Claude Setup | Setup | Check Monday trial status and end date | 1 | Now | Fri 2 Oct |  | Not started | Cat – from the van
2 | 0. Monday & Claude Setup | Setup | Upgrade Monday to Pro, monthly billing | 1 | Now | Fri 2 Oct |  | Not started | Cat – call Charlotte for card
3 | 0. Monday & Claude Setup | Setup | Invite Yahya to Monday as Member (info@infovis.co.uk) | 1 | Now | Fri 2 Oct |  | Not started | Cat to email him once done
4 | 0. Monday & Claude Setup | Setup | Make sure Cat is a Monday admin | 1 | Now | Fri 2 Oct |  | Not started
5 | 0. Monday & Claude Setup | Setup | Send Yahya samples: spreadsheet, task list, marketing plan, targets, enquiry tracker extract | 1 | Now | Weekend |  | Not started | This workbook covers the task list
6 | 0. Monday & Claude Setup | Setup | Setup day with Yahya, Cat and Charlotte | 1 | Now | Mon 5 Oct |  | Not started
7 | 0. Monday & Claude Setup | Setup | Build marketing board – one group per brand | 1 | Now | Mon 5 Oct |  | Not started | Yahya
8 | 0. Monday & Claude Setup | Setup | Load this task list into Monday | 1 | Now | Mon 5 Oct |  | Not started | Yahya
9 | 0. Monday & Claude Setup | Setup | Build goals & targets dashboard for the Tuesday meeting | 1 | Now | Mon 5 Oct |  | Not started | Yahya
10 | 0. Monday & Claude Setup | Setup | Connect Claude to Monday | 1 | Next | Oct |  | Not started | Yahya
11 | 0. Monday & Claude Setup | Setup | Add team to Monday (Danelle, Ana, Lois, Jessica, Alex as needed) | 1 | Next | Oct |  | Not started
12 | 0. Monday & Claude Setup | Setup | Onboard Jessica – email, Monday, Claude (TBC) | 1 | Next | Mid-Oct |  | Not started
13 | 0. Monday & Claude Setup | Setup | Onboard Lois – Monday, Claude Team (email done) | 1 | Next | End Oct |  | Not started
14 | 1. All Brands | Marketing plans | Write a one-page marketing plan per brand: who buys, what we sell, where we find them, monthly targets | 1 | Next | Oct |  | Not started
15 | 1. All Brands | Marketing plans | Set monthly targets per brand – enquiries, bookings, £ booked | 1 | Next | Oct |  | Not started
16 | 1. All Brands | Marketing plans | Track goals completed vs targets – review every Tuesday | 1 | Next | Weekly |  | Not started
17 | 1. All Brands | Marketing plans | Social media content calendar across all brands | 1 | Next | Oct |  | Not started
18 | 1. All Brands | Website | Audit every page on every brand website – wording and what goes where | 1 | Next | From end Oct |  | Not started | First job when Lois starts
19 | 1. All Brands | Website | Check all website wording is right for SEO | 1 | Next | From end Oct |  | Not started
20 | 1. All Brands | Website | Extend website wording where pages are thin | 2 | Later | Nov–Dec |  | Not started
21 | 1. All Brands | Website | Bring case studies up to date on every site | 1 | Next | From end Oct |  | Not started
22 | 1. All Brands | Blogs | Check blogs are generating SEO traffic | 1 | Next | From end Oct |  | Not started
23 | 1. All Brands | Blogs | Blog calendar for each brand | 2 | Later | Nov |  | Not started
24 | 1. All Brands | Client experience | Map the client journey: enquiry → quote → booking → event → follow-up | 2 | Later | Nov |  | Not started | Cat + Lois brainstorm
25 | 1. All Brands | Client experience | Collect reviews after every event – set a simple process | 1 | Next | Oct |  | Not started
26 | 1. All Brands | Brochures | Check every brand has a brochure ready to send | 1 | Next | Oct |  | Not started
27 | 1. All Brands | Mail shots | Mail shot plan for every brand – calendar and contact lists | 1 | Next | Oct–Nov |  | Not started
28 | 1. All Brands | PR | Include BNC in every press release, for every brand | 1 | Now | Ongoing |  | Not started | Use BNC's marketing systems
29 | 1. All Brands | PR | Press release plan for each brand | 1 | Next | Oct–Nov |  | Not started
30 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Confirm exhibition date, venue, stand size and what's included | 1 | Now | Now |  | Not started | Date TBC – end of October
31 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Find out what marketing BNC offers exhibitors – newsletters, social, website listings, press | 1 | Now | Now |  | Not started
32 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Get BNC logos, brand guidelines and exhibitor wording | 1 | Now | Oct |  | Not started
33 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Decide which brands we showcase and how – one Collective stand | 1 | Now | Oct |  | Not started
34 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Stand concept, styling and layout | 1 | Next | Oct |  | Not started
35 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Stand materials – banners, brochures, signage | 1 | Next | Oct |  | Not started
36 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Tasting, demo or experience on the stand | 1 | Next | Oct |  | Not started
37 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Staff rota for the stand | 1 | Next | Oct |  | Not started
38 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Promote our attendance through BNC's marketing channels | 1 | Next | Oct |  | Not started
39 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Promote our attendance on our own social media and mail shots | 1 | Next | Oct |  | Not started
40 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Lead capture on the day – contact details and enquiries | 1 | Next | Event day |  | Not started
41 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Photos and video on the day | 1 | Next | Event day |  | Not started
42 | 1b. BNC Exhibition (end Oct) | BNC Exhibition | Follow up every lead within a week | 1 | Next | Early Nov |  | Not started
43 | 1c. Venue Sourcing | Venue Sourcing | Brainstorm our point of difference – every caterer wants the venues, why us? (Cat, Jessica, Lois) | 1 | Now | Now |  | Not started | Whole Collective as one supplier: food, drink, styling, staffing, wellness, Latino
44 | 1c. Venue Sourcing | Venue Sourcing | Write the point of difference in one line, plus 3 proof points | 1 | Now | Now |  | Not started
45 | 1c. Venue Sourcing | Venue Sourcing | Build the target venue list – type, capacity, current caterer, contact | 1 | Now | Now |  | Not started
46 | 1c. Venue Sourcing | Venue Sourcing | Pick the top 20 venues to go after first | 1 | Next | Oct |  | Not started
47 | 1c. Venue Sourcing | Venue Sourcing | Find out how each venue picks suppliers – preferred supplier lists, tenders, commission | 1 | Next | Oct |  | Not started
48 | 1c. Venue Sourcing | Venue Sourcing | Christmas packages for venues | 1 | Now | Now |  | Not started | Link with PenniBlack Christmas packages
49 | 1c. Venue Sourcing | Venue Sourcing | Supper club packages | 1 | Next | Oct |  | Not started
50 | 1c. Venue Sourcing | Venue Sourcing | Other packages – corporate, launches, wellness days, Latino nights | 1 | Next | Oct–Nov |  | Not started
51 | 1c. Venue Sourcing | Venue Sourcing | Venue brochure / supplier pack | 1 | Next | Oct |  | Not started
52 | 1c. Venue Sourcing | Venue Sourcing | Case studies to show venues | 1 | Next | Oct–Nov |  | Not started | Use Free Spirit at Menier as the model
53 | 1c. Venue Sourcing | Venue Sourcing | Outreach plan – email, call, visit | 1 | Next | Oct |  | Not started
54 | 1c. Venue Sourcing | Venue Sourcing | Invite venue managers to a tasting or showcase | 1 | Next | Oct–Nov |  | Not started
55 | 1c. Venue Sourcing | Venue Sourcing | Venue pipeline board in Monday – contacted, meeting, trial, on supplier list | 1 | Now | Mon 5 Oct |  | Not started | Ask Yahya
56 | 1c. Venue Sourcing | Venue Sourcing | Follow up and get onto preferred supplier lists | 1 | Next | Nov–Dec |  | Not started
57 | 2. PenniBlack Catering & Events | Christmas | Christmas campaign to existing followers – social posts | 1 | Now | Oct–Dec |  | Not started | Big follower base – use it
58 | 2. PenniBlack Catering & Events | Christmas | Christmas mail shot to past clients and followers | 1 | Next | Oct |  | Not started
59 | 2. PenniBlack Catering & Events | Christmas | Christmas packages with 'from £' prices | 1 | Now | Oct |  | Not started
60 | 2. PenniBlack Catering & Events | Christmas | Christmas brochure | 1 | Next | Oct |  | Not started
61 | 2. PenniBlack Catering & Events | Christmas | Fast follow-up on Christmas enquiries and quotes | 1 | Next | Oct–Dec |  | Not started | Danelle + Ana
62 | 2. PenniBlack Catering & Events | Brand activations | Gather photos and case studies from past brand activations | 1 | Next | Oct |  | Not started
63 | 2. PenniBlack Catering & Events | Brand activations | Brand activation pitch – 'we bring your brand to life' | 1 | Next | Oct |  | Not started
64 | 2. PenniBlack Catering & Events | Brand activations | Target list of companies to pitch | 1 | Next | Oct |  | Not started
65 | 2. PenniBlack Catering & Events | Brand activations | Outreach and book meetings with target companies | 1 | Next | Oct–Nov |  | Not started
66 | 2. PenniBlack Catering & Events | Harvest Moon | Write up Harvest Moon as the flagship concept example – photos, story, menu | 1 | Next | Oct |  | Not started
67 | 2. PenniBlack Catering & Events | Harvest Moon | Develop more concepts in the same style for pitches | 2 | Later | Nov–Jan |  | Not started
68 | 3. Free Spirit Wellness | Showcase event | Chase Momoko (Menier Venues) to confirm the date – push hard, nothing can be booked until it's set | 1 | Now | Now |  | Not started | Hoping for Wed 21 Oct
69 | 3. Free Spirit Wellness | Showcase event | Confirm which Menier team members are coming and agree the run of show | 1 | Now | Once date set |  | Not started | Purpose: the Menier team try it and review it
70 | 3. Free Spirit Wellness | Showcase event | Book workshop hosts – Ayurvedic scrubs, yoga, self-defence | 1 | Now | Once date set |  | Not started | Waiting on date
71 | 3. Free Spirit Wellness | Showcase event | Plan the food and menu | 1 | Next | Oct |  | Not started
72 | 3. Free Spirit Wellness | Showcase event | Create a luxury concept and styling – every touchpoint high-end | 1 | Next | Oct |  | Not started | Luxury experience is the brief
73 | 3. Free Spirit Wellness | Showcase event | Videographer and photographer brief and shot list – film the whole experience | 1 | Next | Oct |  | Not started
74 | 3. Free Spirit Wellness | Showcase event | Capture video testimonials and written reviews from the Menier team | 1 | Next | Event day |  | Not started
75 | 3. Free Spirit Wellness | After the event | Write the case study | 1 | Next | After event |  | Not started
76 | 3. Free Spirit Wellness | After the event | Marketing campaign to venues showing what we can do | 1 | Next | After event |  | Not started
77 | 3. Free Spirit Wellness | After the event | Free Spirit brochure / venue pack | 1 | Next | After event |  | Not started
78 | 3. Free Spirit Wellness | After the event | Add case study and gallery to website | 2 | Later | Nov |  | Not started
79 | 3. Free Spirit Wellness | Research | Research what's trending in the wellness industry | 2 | Later | Nov |  | Not started
80 | 4. Pichi | Launch follow-up | Send Momoko (Menier Venues) the full attendee list from the Pichi launch | 1 | Now | Mon 5 Oct |  | Not started | Promised in Charlotte's email of 1 Oct – Cat
81 | 4. Pichi | Launch follow-up | Use launch photos and videos for a case study and social posts | 1 | Next | Oct |  | Not started | Quick win
82 | 4. Pichi | Vision | Brainstorm sessions with Steph, Raquel and Ana | 2 | Later | Oct–Nov |  | Not started
83 | 4. Pichi | Vision | Define the Pichi vision – music, food, energy, Zumba, all of Latino culture | 2 | Later | Nov |  | Not started
84 | 4. Pichi | Website | Plan the website structure | 2 | Later | Nov |  | Not started
85 | 4. Pichi | Website | Write all website wording | 2 | Later | Nov–Dec |  | Not started
86 | 4. Pichi | Website | Build and launch the website | 2 | Later | Dec–Jan |  | Not started
87 | 4. Pichi | Marketing | Pichi marketing materials – brochure and social templates | 2 | Later | Nov |  | Not started
88 | 4. Pichi | Marketing | Pichi social media pages and content | 2 | Later | Nov |  | Not started
89 | 5. Raquel's Staffing & Bar | Marketing plan | Marketing plan built on 'we make people look cool' | 1 | Next | Oct |  | Not started
90 | 5. Raquel's Staffing & Bar | Showcase | Photoshoot of the regular team – the great faces and attitude | 1 | Next | Oct |  | Not started
91 | 5. Raquel's Staffing & Bar | Showcase | Team profiles and social posts featuring the staff | 1 | Next | Oct–Dec |  | Not started
92 | 5. Raquel's Staffing & Bar | Sales | Staffing brochure for venues and agencies | 1 | Next | Oct |  | Not started
93 | 5. Raquel's Staffing & Bar | Sales | Target list of venues, agencies and event companies | 1 | Next | Oct |  | Not started
94 | 5. Raquel's Staffing & Bar | Sales | Christmas staffing push to venues | 1 | Next | Oct–Nov |  | Not started
95 | 5. Raquel's Staffing & Bar | Sales | Collect client reviews | 1 | Next | Ongoing |  | Not started
96 | 6. VENN Productions | Content | Gather photos and videos of past VENN work | 2 | Later | Nov |  | Not started
97 | 6. VENN Productions | Content | Content showcasing Jess and Dave's eye and styling ideas | 2 | Later | Nov–Dec |  | Not started
98 | 6. VENN Productions | Content | VENN case studies | 2 | Later | Nov–Dec |  | Not started
99 | 6. VENN Productions | Sales | VENN brochure | 2 | Later | Dec |  | Not started
100 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: marketing plan – its own plan, targets and audience (schools) | 1 | Next | Oct |  | Not started | Separate from Youth
101 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: bring the wellness wheel to life – content explaining each part | 1 | Next | Oct–Nov |  | Not started
102 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: introduce Be-Zing Kids to schools – intro pack / email | 1 | Next | Oct–Nov |  | Not started
103 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: build a schools contact list | 1 | Next | Oct |  | Not started
104 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: Christmas ideas for schools | 1 | Next | Oct |  | Not started
105 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: design the end-of-year competition – theme, rules, prizes | 1 | Next | Oct–Nov |  | Not started
106 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: launch the competition to schools by January | 1 | Next | By Jan |  | Not started
107 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: plan the award ceremony with the wellness wheel animals | 2 | Later | Jan |  | Not started | Check details with Charlotte
108 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: back-to-school ideas for next term | 2 | Later | Dec |  | Not started
109 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: mail shots to schools | 1 | Next | Nov–Jan |  | Not started
110 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: social media pages and content | 2 | Later | Nov |  | Not started
111 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: blogs | 2 | Later | Nov–Jan |  | Not started
112 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: brochure / schools pack | 1 | Next | Nov |  | Not started
113 | 7. Be-Zing (Kids + Youth) | Be-Zing Kids | Kids: website wording | 2 | Later | Nov–Dec |  | Not started
114 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: marketing plan – its own plan, targets and audience | 2 | Later | Nov |  | Not started | Separate from Kids
115 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: market the DofE courses to schools and DofE centres | 2 | Later | Nov–Jan |  | Not started
116 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: market the creative courses | 2 | Later | Nov–Jan |  | Not started
117 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: start TikTok | 2 | Later | Nov |  | Not started
118 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: social media pages and content | 2 | Later | Nov |  | Not started
119 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: mail shots | 2 | Later | Nov–Jan |  | Not started
120 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: blogs | 2 | Later | Nov–Jan |  | Not started
121 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: course brochure | 2 | Later | Nov |  | Not started
122 | 7. Be-Zing (Kids + Youth) | Be-Zing Youth | Youth: website wording and course pages | 2 | Later | Nov–Dec |  | Not started
123 | 8. The Edit (PBC Edit) | The Edit | Define the concept and sections – luxury catering, Latino culture, wellness, styling, staffing, youth | 2 | Later | Nov |  | Not started | 'You've seen it here first'
124 | 8. The Edit (PBC Edit) | The Edit | Gather content and photos from every brand | 2 | Later | Nov |  | Not started
125 | 8. The Edit (PBC Edit) | The Edit | Write the copy | 2 | Later | Nov–Dec |  | Not started
126 | 8. The Edit (PBC Edit) | The Edit | Design it using the brand identities in Claude Design | 2 | Later | Dec |  | Not started
127 | 8. The Edit (PBC Edit) | The Edit | Plan distribution – print, digital, mail shot | 2 | Later | Dec–Jan |  | Not started
128 | 9. Systems & Admin | Team calendar | Team availability calendar in Monday – who's free to work when | 1 | Now | Oct |  | Not started | Quick win – ask Yahya
129 | 9. Systems & Admin | Finance | Connect Xero to Monday and Claude | 2 | Later | Nov |  | Not started | Yahya
130 | 9. Systems & Admin | Finance | Integrate financial plans and targets | 2 | Later | Nov–Dec |  | Not started
131 | 9. Systems & Admin | Stock control | Pull together the stock list | 2 | Later | Nov |  | Not started
132 | 9. Systems & Admin | Stock control | Scope and build the stock control system (trial) | 2 | Later | Nov–Jan |  | Not started | Alex
133 | 9. Systems & Admin | Stock control | Packing lists and processes | 3 | Later | 2027 |  | Not started
134 | 9. Systems & Admin | Hygiene & safety | Review the hygiene and safety systems | 3 | Later | 2027 |  | Not started
135 | 9. Systems & Admin | Hygiene & safety | Bring hygiene and safety files into one place | 3 | Later | 2027 |  | Not started
136 | 9. Systems & Admin | Staffing systems | Database review of the Replit staff app | 3 | Later | 2027 |  | Not started | Yahya
137 | 9. Systems & Admin | Staffing systems | Staff app – shifts, clocking in/out, pay, documents | 3 | Later | 2027 |  | Not started
138 | 9. Systems & Admin | Staffing systems | Timesheets feeding into payroll | 3 | Later | 2027 |  | Not started